## Readiness_Checklist
PayFix AI 2.0 — Step 31 UAT Execution Readiness
[7 empty] | Readiness Summary | Count
Overall Readiness Decision | NOT READY FOR FULL-SERVICE UAT EXECUTION | [5 empty] | Ready | 7
[7 empty] | Not Ready | 8
Readiness ID | Readiness Criterion | Current Status | Evidence / Basis | Owner | Action Required | Notes
RDY-01 | Requirements baseline available | Ready | Step 24 Requirements Baseline | Business Analyst | None | Baseline established.
RDY-02 | Product backlog and story traceability available | Ready | Step 25 Product Backlog | Business Analyst | None | Backlog traceability available.
RDY-03 | UAT strategy defined | Ready | Step 29 Business Testing and UAT Strategy | Business Analyst | None | Strategy and acceptance principles documented.
RDY-04 | Detailed UAT cases designed | Ready | Step 30 Requirements-to-Test Traceability | Business Analyst | None | 20 structured UAT cases designed.
RDY-05 | Synthetic test data approach available | Ready | Step 16 synthetic data + Step 30 test design | Business Analyst | None | Synthetic-only portfolio approach retained.
RDY-06 | Complete service implemented in representative test environment | Not Ready | Complete service not implemented | Engineering / Delivery | Implement agreed scope in representative test environment | Full-service execution cannot begin.
RDY-07 | Required system and integration testing completed before UAT | Not Ready | Full system not implemented | QA / Engineering | Complete prerequisite system/integration assurance | No fabricated prerequisite test results.
RDY-08 | UAT users and authorised business testers assigned | Not Ready | Portfolio project; no live business testers assigned | Product / Business | Assign authorised business testers in real delivery context | No real-user participation claimed.
RDY-09 | Required user roles and test access provisioned | Not Ready | Representative environment unavailable | Engineering / Security | Provision controlled UAT access and roles | Access must reflect authority model.
RDY-10 | Defect workflow defined | Ready | Step 31 defect-management design | Business Analyst / QA | None | Workflow and severity model defined.
RDY-11 | Evidence capture approach defined | Ready | Steps 29–31 | Business Analyst / QA | None | Evidence references are built into execution and retest logs.
RDY-12 | Business approver identified for formal acceptance | Not Ready | No live organisational approver | Product / Business | Nominate authorised business approver | Portfolio owner is not treated as live business approver.
RDY-13 | Security/privacy assurance sufficient for UAT scope | Not Ready | Formal assurance not yet performed | Security / Privacy | Complete applicable assurance before UAT entry | Step 32 will define the assurance approach.
RDY-14 | Critical dependencies or controlled stubs available | Not Ready | Representative integrations unavailable | Engineering / Delivery | Provide required dependencies/stubs | No production integration is claimed.
RDY-15 | UAT entry decision recorded | Not Ready | Entry criteria not satisfied | Business / Product | Record decision only after readiness criteria are met | Current decision remains Not Ready.

## UAT_Execution_Log
PayFix AI 2.0 — Full-Service UAT Execution Log
Current position: Full-service UAT has not started. All results remain Not Executed. Step 28 prototype evidence for UAT-17 to UAT-20 is supporting evidence only and is not full-service UAT.
Execution ID | Test Case ID | Test Case Title | Requirement IDs | Story IDs | Tester | Execution Date | Environment | Actual Result | Result | Evidence Reference | Defect ID | Comments
EXE-01 | UAT-01 | Create new dispute | BR-001, UR-CUS-002, FR-003, DR-001, DR-003 | US-001, US-003 |  |  |  |  | Not Executed
EXE-02 | UAT-02 | Request missing evidence | BR-005, BR-008, UR-CUS-001, UR-CUS-004, FR-008, FR-010, FR-011, DR-015, DR-016, DR-017, UXR-008, UXR-009, UXR-012, UXR-013 | US-007 |  |  |  |  | Not Executed
EXE-03 | UAT-03 | Receive requested evidence | BR-005, BR-010, BR-011, FR-011, FR-024, DR-011, DR-012, DR-013, DR-015, DR-016, DR-017 | US-007, US-020 |  |  |  |  | Not Executed
EXE-04 | UAT-04 | Transfer queue ownership | BR-004, BR-010, BR-011, FR-018, FR-019, DR-024, DR-025, UXR-029, UXR-030 | US-015 |  |  |  |  | Not Executed
EXE-05 | UAT-05 | Create specialist referral | BR-006, BR-010, BR-011, FR-027, DR-026, DR-027, UXR-029, UXR-030, CR-008, CR-012 | US-023 |  |  |  |  | Not Executed
EXE-06 | UAT-06 | Accept specialist referral | BR-006, BR-010, BR-011, FR-028, DR-028, DR-029, CR-008, CR-012 | US-024 |  |  |  |  | Not Executed
EXE-07 | UAT-07 | Record dispute decision | BR-007, BR-011, FR-035, DR-032, DR-033, DR-034, CR-001, CR-002, CR-003, CR-004, CR-009 | US-031 |  |  |  |  | Not Executed
EXE-08 | UAT-08 | Complete approval | BR-007, BR-011, UR-FIN-001, FR-036, CR-001, CR-002, CR-003, CR-004, CR-009, CR-010 | US-032 |  |  |  |  | Not Executed
EXE-09 | UAT-09 | Communicate authorised outcome | BR-008, BR-011, UR-CUS-009, FR-042, DR-036, DR-037, UXR-023, UXR-024, UXR-025, UXR-026, UXR-027, UXR-028 | US-038 |  |  |  |  | Not Executed
EXE-10 | UAT-10 | Close eligible case | BR-011, BR-014, FR-047, DR-038, CR-011, CR-012 | US-043 |  |  |  |  | Not Executed
EXE-11 | UAT-11 | Complaint/dispute separation | BR-011, BR-013, UR-COM-001, FR-044, FR-045 | US-040, US-041 |  |  |  |  | Not Executed
EXE-12 | UAT-12 | Conflicting information | BR-003, BR-012, FR-009, FR-013, DR-014, DR-015, DR-043, CR-006, CR-007, CR-008, CR-012 | US-049 |  |  |  |  | Not Executed
EXE-13 | UAT-13 | Missing current ownership | BR-004, BR-010, FR-017, DR-021, DR-022, CR-008, NFR-013 | US-014, US-046 |  |  |  |  | Not Executed
EXE-14 | UAT-14 | Prevent wrong-case association | DR-006, DR-011, DR-012, DR-013, CR-017, NFR-019 | US-018, US-045 |  |  |  |  | Not Executed
EXE-15 | UAT-15 | Prevent unauthorised action | BR-007, CR-001, CR-002, CR-003, CR-004, CR-017, NFR-001, NFR-002 | US-032, US-052 |  |  |  |  | Not Executed
EXE-16 | UAT-16 | Automation unavailable | BR-012, BR-015, FR-049, DR-042, CR-014, NFR-008, NFR-016 | US-054, US-055 |  |  |  |  | Not Executed
EXE-17 | UAT-17 | Generate Evidence Summary | DR-048, DR-049, UXR-031, UXR-035, AIR-001, AIR-003, AIR-004, AIR-005, AIR-006, AIR-013, AIR-016 | US-061 |  |  |  |  | Not Executed |  |  | Step 28 prototype evidence exists separately; this row represents future full-service UAT execution.
EXE-18 | UAT-18 | Human review Evidence Summary | DR-049, UXR-036, AIR-006, AIR-007, AIR-008, AIR-013, AIR-016 | US-062, US-063 |  |  |  |  | Not Executed |  |  | Step 28 prototype evidence exists separately; this row represents future full-service UAT execution.
EXE-19 | UAT-19 | Generate Handoff Summary | DR-048, DR-049, UXR-031, UXR-035, AIR-001, AIR-003, AIR-004, AIR-005, AIR-006, AIR-013, AIR-016 | US-064, US-065 |  |  |  |  | Not Executed |  |  | Step 28 prototype evidence exists separately; this row represents future full-service UAT execution.
EXE-20 | UAT-20 | AI unavailable/unusable | FR-050, DR-049, NFR-009, AIR-002, AIR-008, AIR-013, AIR-016 | US-063, US-066 |  |  |  |  | Not Executed |  |  | Step 28 prototype evidence exists separately; this row represents future full-service UAT execution.

## Defect_Log
PayFix AI 2.0 — UAT Defect Log
No full-service UAT defects have been raised because full-service UAT has not been executed.
Defect ID | Related UAT ID | Requirement / Story IDs | Defect Summary | Defect Description | Severity | Business Impact | Status | Raised By | Raised Date | Assigned Owner | Fix Reference | Retest Required | Final Disposition | Evidence Reference | Notes

## Retest_Log
PayFix AI 2.0 — Defect Retest Log
No retest activity has been recorded because no full-service UAT defects currently exist.
Retest ID | Defect ID | UAT Test Case ID | Fix Reference | Retest Preconditions | Retest Steps | Expected Result | Actual Result | Retest Outcome | Tester | Retest Date | Evidence Reference | Notes

## UAT_Signoff
PayFix AI 2.0 — UAT Business Acceptance and Sign-off
Field | Value
Project | PayFix AI 2.0
UAT Scope | Full-Service Business UAT
UAT Execution Status | Not Started
Critical Scenarios Executed | No
Outstanding Critical Defects | Not Assessed
Outstanding High Defects | Not Assessed
Residual Risks Reviewed | Not Performed
Business Acceptance Decision | Not Available
Acceptance Conditions
Business Approver
Approval Date
Production Approval | Not Granted
Sign-off rule: Business acceptance may only be recorded after agreed UAT scope has actually been executed, evidence reviewed, material defects dispositioned and residual risks formally considered by an authorised business representative.